## Slide 1
CONSTRUCTION LEGAL ISSUES & COVID19
Michael Hiscock, Partner 24/4/20

## Slide 2
| Important issues
Business continuity
Payment
Extensions of Time
Loss and expense
Health and safety
Availability of goods and materials
Availability of consultancy team
Avoiding or managing disputes
What does the contract say?

## Slide 3
| JCT Design and Build 2016 (unamended)
Extensions of time
Give notice whenever it becomes reasonably apparent that progress will be delayed, setting out material circumstances and causes, identify the Relevant Event.
As soon as possible thereafter give more detail on expected effects – if estimated, keep updating the information - show cause and effect, keep records.
Fair and reasonable extension decision in 12 weeks or prior to PC.
After PC – employer 12 week review of EoTs.
Contractor must constantly use best endeavours to mitigate.

## Slide 4
| JCT DB16
Relevant Events:
Changes
Employer impediment
Change in law
Force majeure
Instruction to postpone
Deferred site possession
Suspension for non payment
]

## Slide 5
| JCTDB16
Loss and Expense
Must notify as soon as likely loss and expense becomes reasonably apparent
As soon as reasonably practicable submit initial assessment of loss incurred and any likely further amount with reasonable supporting information.
Contractor must update that information at monthly intervals – Employer must reply to each update within 14 days, notifying assessment
Condition Precedent ?

## Slide 6
| JCTDB16
Relevant Matters:
Changes
Instruction to postpone works
Employer Impediment
Changes
Addition, omission, substitution, alteration of type or standard of materials.
Imposition by Employer of limitations of site access, working hours,
space to work, order of work, substantial change in conditions.

## Slide 7
| JCTDB16
Change in Law:
Change in Statutory Requirements after the Base Date that necessitates an alteration or modification to the Works = Change (time and money)
Exercise by Government after Base Date of any statutory power that affects the execution of the Works = Relevant Event (time only)
Change in goods (“so far as procurable”)
CDM Regulations 2015
Client has to make arrangements to protect health and safety as far as reasonably possible.
Contractor as PD or PC can issue a notice of reasonable objection to Changes on health and safety grounds.
Coronavirus Regulations / CLC SOP v3
Avoid working closer than 2m where possible but if not possible, take steps to protect workforce
Coro

## Slide 8
| JCTDB16
Payment
Apply for payment on time, provide enough information to explain application, issue payment notice on time, issue pay less notice on time, consider format and content of notices. Cabinet Office PPNs
Contracting authorities are encouraged to consider flexing payment, looking at KPIs, adjusting milestones, considering advance payment, using procurement cards, paying on order not delivery – but this is guidance, not law.

## Slide 9
| NEC3/4 (unamended)
Early Warning Notices
Contractor and Project Manager notify eachother as soon as either becoe aware of possible increase in total Prices, delay to Completion, delay achieving Key Date, impair performance of works once in actual use.
Compensation Events assessed as if Early Warning Notice given. Risk Register / Risk Reduction Meetings
Used as a reference but entitlement to time and money comes through
Compensation Events

## Slide 10
| NEC3/4
Must notify with 8 weeks of becoming aware of the event (NEC3) / becoming aware that event has happened (NEC4) – condition precedent.
A failure by the PM to respond to a claim within 2 week warning period is deemed acceptance.

## Slide 11
| NEC3/4
Compensation Events
Change to Works Information
Delayed access to site
Instruction to stop or not to start works
Employers risk event as stated in Contract Data
Employer breach.
An event which norther party could prevent and which an experienced contractor judged so small a risk that it was unreasonable to allow for it.
(Also see 19 – prevention.)

## Slide 12
| NEC3/4
Options
X2 – change in law
SPIRIT OF MUTUAL TRUST AND COOPERATION
Clause 10.1 / Option X12 partnering
Costain v Tarmac 2017 TCC
Coulson J – “do not attempt to improperly exploit the situation or mislead the other party” – “correct an obviously false assumption”
]

## Slide 13
| Disputes
Adjudication and insolvency
Bresco Electrical Services v Lonsdale / Cannon V Primus
Bresco appeal to the Supreme Court – heard this week by virtual hearing with 5 Justices – awaiting their Lordships’ judgment.
Court of Appeal – where a company is in liquidation, the adjudication is futile – where the company is in CVA, they might trade out so adjudication can proceed.
Meadowside Building v Hill Street Management
High Court – an adjudication could proceed to determine the final net position between the parties as long as adequate security is provided by the insolvent company to secure the money and allow the temporary binding adjudicator’s award to be challenged in court
]

## Slide 14
| Disputes
Smash & Grab Adjudication
Obtaining payment based on a procedural non compliance - eg late service of payment notice
Grove Developments v S & T
Court of Appeal – the paying party must pay the award and then commence a true value adjudication
Coronavirus in the TCC MillChris Developments v Waters – April 2020
Developer sought an injunction to stop an adjudication arguing breach of natural justice because it would face difficulties obtaining evidence from its own staff and its expert in time, due to lockdown.
Injunction refused – logistical issues not sufficient – records can be held electronically. However – decision was fact based – what if the staff were in hospital ? Want if adjudicator called a hearing or a site visit but the key witness was ill ? We await post-award enforcement arguments based on Covid 19 unfairness.
]

## Slide 15
| Disputes
Proving a claim
Records, records, records
Events – critical path – causation – notice procedures
JCT – retrospective analysis / NEC – prospective analysis
Concurrent delay – truly concurrent, of equal causative potency – (harsh) express contract clause is permitted to place risk on contractor
]

## Slide 16
|
Wright Hassall
April 2020
Please note the information in this talk is generic legal training only and should not be used as a substitute for detailed legal advice on a specific issue.
]